## ProductBacklog
Project Name | Blood Bank Today
Client | Blood Bank Today
Created By | Edubridge
Creation | DD/MM/YYYY
Approvals Date | DD/MM/YYYY
Epic | User Story Id | Features/Title | User Story/Requirements | Status | Acceptance Creteria
Blood Bank Today_001: Checking the functionalities of Registration,Login and Logout | US001 | Registration | As a first time visitor to Blood Bank Today website, I want to register my account,so that I can login to the application. | New | New user should able to register account with valid data.
| US002 | Login | As a Registered user I want to login to website so that I can see my account details…etc | New | User should able to Login with valid credentials.
| US003 | Logout | As a Registered user I want to logout from my account so that no one else can't access my account | New | User should able to Logout.

## Sprint Backlog
Project Name | Blood Bank Today
Client | Blood Bank Today
Created By | Edubridge
Creation | DD/MM/YYYY
Approvals Date | DD/MM/YYYY
Epic | User Story Id | Features/Title | User Story/Requirements | Status | Acceptance Creteria | Story Point/Duration: (Hours/Days | Sprint
Blood Bank Today_001: Checking the functionalities of Registration,Login and Logout | US001 | Registration | As a first time visitor to Blood Bank Today website, I want to register my account,so that I can login to the application. | New | New user should able to register account with valid data. | 15 | 1
| US002 | Login | As a Registered user I want to login to website so that I can see my account details…etc | New | User should able to Login with valid credentials. | 15 | 1
| US003 | Logout | As a Registered user I want to logout from my account so that no one else can't access my account | New | User should able to Logout. | 10 | 1

## Tasks
Design & Developer | Tester
Understanding BRS,SRS | Understanding BRS,SRS
Design | Writing Test Scenario and Test Cases
Coding | Test Environments Setup
Unit Testing | Test Execution
Integration Testing | Defing Defect
Code Review | Re-Testing
Bug Fixing | Automation
Team Meetings | Team Meetings